## Outline
Develement Roadmap (feedback, features, featurelocks, and roadmap)
Different from TODO list which is update specific active/reactive update bugs, features, and done so far.
This roadmap is proactive, critical and directed thinking for best future development for the game.
This is apposed to just working on spur of the moment easy and fun things when I want to
May take the form of a better list
[8 empty] | ✔ | 30 mins
2019-09-01 | [7 empty] | X | Missed
Mon | Tue | Wed | Thur | Fri | Sa | Sun | Total | 45 | Mins total worked on
9 - | 10 - ✔ Made feature lock tab | 11 - 60 Added almost all features to list | 12 - 45 Recorded Erik+Brian Music, added music to game, worked on pygame display while reading documentation. | 13 - ✔ Started going through old TODO lists. | 14 - 45 going through lists, still need to go through written work then clean up the actual list before priority and breaking down big ones. | 15 - 120 Attempted to make game playable by changing sound effects, realized will be unplayble until inbetween build, layed game without secrets to look for feedback and balance (file called Doug for Alpha0.29, made file in balance folder, Added last things from google keep notes | 330
16 - X | 17 - 45 finished feature lock list, needs descr. Cleanup, feedback, and review | 18 - 90 Cleaned up features list, started going through and combining with feedback | 19 - ✔ Finished integrating feedback and integrating TODO list | 20 - | 21 - | 22 - |  | Would like to finish feature lock at least and get into breakdown
23 - | 24 - | 25 - | 26 - | 27 - | 28 - | 29 - |  | Breakdown
30 - | 1 - | 2 - | 3 - | 4 - | 5 - | 6 - |  | Feature lock release Oct 1?

## Feedback
Feedback | Priority | Links | When Reported (update) | Est Implement Time (hrs) | Description (64 char max) | Details | What kind of game it makes (who) | Priorities |  | -
13 | ~ |  | 0.28 | 1 | Song doesn't play when restarts |  |  | - | Not set yet | ~
14 | ~ |  | 0.28 | 0.75 | 3rd floor thode up (only go if exists error catch) |  |  | ~ | Bug | ↑
18 | ~ |  | 0.28 | 0.75 | UH Big Hits shirt inspect glitch |  |  | ★ | Must Have | ↑↑
3 | ★ |  | 0.28 | 0.25 | Look Around (Rod) |  |  | ✔ | Try, see how far | →
5 | ★ |  | 0.28 | 0.25 | No Empty name excepted (Zac) |  |  | ☺ | Nice to Have | ↓
6 | ★ |  | 0.28 | 0.25 | "B is back" (Zac) |  |  | X | Not for this update | ←
7 | ★ |  | 0.28 | 2 | Spelling/grammer (Zac, |  |  |  |  | ★
8 | ★ |  | 0.28 | 0.25 | "Dell, Intel Inside" |  |  |  |  | ☺
10 | ★ |  | 0.28 | 0.75 | Short word for verbs, for inv, s for stats |  |  |  |  | ✔
11 | ★ |  | 0.28 | 0.25 | Wear earphones on head |  |  |  |  | X
19 | ★ |  | 0.28 | 0.25 | "search is room, inspect is individual item"
21 | ★ |  | 0.28 | 0.25 | 3W text in QT
35 | ★ |  | 0.28 | 0.25 | Angus, Beef, Barber ("Call me a liar")
43 | ★ | Music | 0.28 | 0.5 | Belzabad plays when you fight kleiman
46 | ★ |  | 0.28 | 1.5 | Fix all text problems or make more auto text mechanics to improve playability
48 | ★ |  | 0.29 | 0.5 | Have Brendan Fallon character with eclipse mug, rocketry t-shirt, Strainer on head?SafetyGlasses?, and iron ring (more characters)
2 | ☺ |  | 0.28 | 4 | *Keep track/quest progress bar (Rod)
12 | ☺ |  | 0.28 | 0.5 | Add Nicole to EP office
15 | ☺ |  | 0.28 | 2 | Auto save every once and a while | I kinda disagree with this one for now. Don't think it should autosave
24 | ☺ | GUI | 0.28 | 3 | Size of window (ascii art print)
30 | ☺ |  | 0.28 | 2 | Wacky items are good
31 | ☺ | GUI | 0.28 | 2 | background/text colours
32 | ☺ |  | 0.28 | 0.5 | 3BB PID with MSP430
33 | ☺ |  | 0.28 | 1.5 | Measure Alice or Bob & they collapse
34 | ☺ |  | 0.28 | 0.5 | put DOD in game
36 | ☺ | Balance | 0.29 | 6 | Balance | * Right now defense is v important but with healing items added this should fix it * Better head items plz * Need story arc for body armour
38 | ☺ |  | 0.28 | 1.5 | Text | * When you inspect the car it says 'Ya thought these were the keys' * When you searching when nothings there "You double take and there's still nothing there" (If you search 20 times you die)
40 | ☺ |  | 0.28 | 5 | More use of storyline, music, definition to people to give realism to the world
42 | ☺ |  | 0.27 | 0.5 | SharpExchange | After giving dirty needle to sharp exchange a random encounter with a person that says "You're the greatest semaritan in the world" and gives you and Uzi
44 | ☺ |  | 0.28 | 2 | Expand on the Story and the high council so they can piece everything together
45 | ☺ |  | 0.28 | 3 | Put item descriptions to have items help tell the story
4 | ✔ |  | 0.28 | 1.5 | Eat People (Arth), depending on who you eat you die
16 | ✔ | GUI | 0.28 | 4 | Arrow keys & WASD moves
17 | ✔ |  | 0.28 | 2 | attack/eat rules sign/interactactables
28 | ✔ | Inventory | 0.28 | 2.5 | Quest inv. Vs other inventory
37 | ✔ |  | 0.28 | 2 | Queues | * Need to know that Jana has the textbook, maybe the story should say that somewhere * Not obveous that equip means to pick up * Phil says that need to be pushed more toward the Phenoix (more people you talk to, or items, tell story about the Phoneix)
47 | ✔ |  | 0.28 | ? | Tyler wants it to be Sandbox mode, no linear stuff, events unfold from there
50 | X |  | 0.29 | 4 | Easier way to access game, not just goo.gl/iK8dL9 (Website maybe)
1 | X |  | 0.28 | 5 | Combat (Vuk)
9 | X |  | 0.28 | 3 | Say short name to pick thing
20 | X |  | 0.28 |  | Starting difficulty hard (won't put in for 2017-2018)
22 | X |  | 0.28 |  | Directions are disorienting
23 | X |  | 0.28 | 3 | Map with items come up
25 | X |  | 0.28 |  | Combat is risky
26 | X | Combat | 0.28 | 4 | Better eating/prep.
27 | X | Money | 0.28 |  | Peter as a vendor
29 | X | Inventory | 0.28 | 4 | Back Pack
39 | X |  | 0.28 | 3 | Notes option (a list of all lore you've gone through)
41 | X |  | 0.28 | 5 | Some sort of skill component to fighting
49 | X |  | 0.28 | ? | AR version of the game -Ekamada
Put into feature lock |  |  |  |  | aaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaa

## Alpha 0.30 Feature Lock
Alpha 0.30 - Kipling Update - Last EPTA Update Feature Lock
Leave It or Evolve It
Feature | 0.30 Priority | Links | Est Implement Time (hrs) | Description (64 char max) | Details | When to implement(update) | What kind of game it makes | Who would play this game | Priorities |  | A-Z (best) | Z-A | Extra
1 | X | All Future, Online, Getting Devs, Multiplayer | BD, 50? | Rebuild Game Engine | * Classes, object methods, how map works (numbered adjacency lists), commenting code. Updating to python 3. Interactables class. Buildings as an entity. * PP8 style using PyCharm * Get rid of global variables and restructure code * Using and understanding effecient python code chunks (See Liam F. and his book) * Make an entity class (name, description, location, stats, health, item need, item give, inventory, deathtext, etc) and then all subclasses using inheritance * Entity Person(each has same attributes and stuff, even schedule would be the same) Boss? Place Interroor Item Interactable Interactable can go, just add a moveable flag to items with new entity structute that allows give/take * See TODO list for rest of rebuild notes | B 0.31 | Consistant, less bugs, well documented, easy to develop | A developer | - | Not set yet | - | X | -
2 | ★ |  | 1.5 | PAP Unlock | * Make PAP unlock when you get to end of game * Unlocked by finishing all of the game * Sound of lightening * followed by the sounds of cowboys * Looks like you need to give something to get something in return * PAP EXP level | 0.30 | Lots of content, adds reward for finding everything | A completitionist, pushing the limits | ~ | Bug | ~ | ✔ | ~
3 | ★ | Future expansions, dungeons, kipling, tutorial room, etc | 2 | Interriors Implement | * Make a basic interrior of bsb and fully test. * Then make all multilevel buildings an interrior * Shouldn't be in here but also from load screen Allow you to save as/copy, and delete files | 0.30 | More conent, better devloped | Someone who likes to explore and find secrets, also dungeon runner | ★ | Must Have | ★ | ☺ | ↑
4 | ☺ |  | 2 | Nonsense Update | * Adding your dad, Alex Jones, Arnold, Jesse Ventura, auto turrets etc, harry potter ring that can talk to the dead * Even more secret place under okons storage place. Leads to underground base. * Mike the liar random event. Running across campus saying stuff. Comments on 4th wall things about the game ex) "They need an autocomplete" * Stackable Visor Glasses * Brendan's jacket holds things in the game scuba Steve (and it's Haugen) | 0.30 ? | Lots of easter eggs and loor | Our friends lol | ✔ | Try, see how far | ☺ | ★ | ↑↑
5 | ☺ |  | 15 | Bio Cards | * Adding explinations to all jokes and inside things to keep game relavent. Not sure if this would take away from game OR if you would only play the year you have it. Idk. * When characters die they drop bio cheet and what their interests are (credits like a great help for devloping game) * Add better biosheet, description of items to explain jokes, a tutorial, and more help to have players finish the game and enjoy it | 0.34 ? | Someone who likes lore | Future Eng Phys people | ☺ | Nice to Have | ✔ | ~ | →
6 | ✔ |  | BD, 10? | Experience Levels + Mobs | * Adding an experience level to the game and mobs that respawn so you feel like you're progressing. Probably buffs stats and helps you beat higher level people/things. Also the respawn with golden gauntlet thanos for Paul the buss driver. * In general, have more crazy/dangerous things happen as you progress in quests/storyline (sand worms pop up, idk, crazyness) * Could have random drop loot * Having fire with cooking be able to cook multiple types of foods (Eggs, meat, bread, ) with BOTW sound * Having more combinations of cooking food * Having more Runescape cooking, experience levels to unlock/burn less, burn levels, etc | 0.30 | More RPG style and feel like you're progressing | RPGs, grindy people etc | X | Not for this update | X | - | ↓
7 | ✔ | Text printer, Colour options, Ascii art generator, rescalable content | BD, 30? | GUI | * Adding map and all suplementary info to the GUI (maybe whole game?) so we can customize content. * IDK. I like idea of two window system with map, player icon, pictures, etc on side. * Size of window (ascii art print) | 0.30 | Easier on eyes, customizable, well refined | RPGers |  |  |  |  | ←
8 | X | All Future | BD, 40? | Online SinglePlayer | * Make game run in javascript/whatever online so you can play game online. * Also has QT scoreboard so more compeditive | 0.33 ? | Easy to access and play anywhere, easy to track and expand to other people | Mobile gamers, anynonwindows/don't want to download. Basically any loose gamer. Also compeditive side online | BD = task needs to be broken down to be more specific |  |  |  | ★
9 | X | All Future Updates | BD, 40? | Online MultiPlayer | * Make other players be able to interact, fight, talk to eachother | 0.35? | MMORPG | People who play MMOs, grindy people, compeditive, etc |  |  |  |  | ☺
10 | ✔ |  | 9 | Input (fast Addressing) | * Make keywords shorter, have list of items to choose from quickly [1-2], maybe accept short names? * Maybe take cardinal coords. * More things rather than equip. * Also possibly controller support? * Short word for verbs, for inv, s for stats * Try having WASD and other key accepts (maybe arrow keys) on the GUI acceptable |  | Well thought out, easier to player and higher skill cap | Speedrunners, first time players, etc |  |  |  |  | ✔
11 | X |  | BD, 25? | Overhauled Combat | * See 13 Hollywood Productions March 7th large section of ideas. * Make combat more turn based with actions, reactions, preps, combos, etc. * Maybe some skill involved? * Mashing a key to beat someone. * At least for now someone comes back for round two. * Every Person has their own weakness/strengths. * Use Darksouls style damage system * Bullet time * Maybe have speed play more of a factor, maybe balance in other ways * Name everything and attack dialougs (use x to do y) | 0.32? | Pokemon style, some darksouls ellements, more skill based | People who like grinding, more professional gamers, etc |  |  |  |  | X
12 | ✔ |  | BD, 15+10+8+15+20? | 2019 Kipling Update | *Year selector * tutorial * intro * Map/characters ( Measure Alice or Bob & they collapse, also DOD) * BSB Dungeon * storyline/quests. This is a substantial piece of work * See Google Keep notes on the story | 0.30 | A game for future Eng Phys Generations. Let's me separate last year's content and this year's content. | Eng Phys friends, Me
13 | ✔ | 2019 Intro | 10 | Music + Compile | * Allow Sounds to play * transitions and have * different music for different settings * Belzabad plays when you fight kleiman * Channel Orange by Frank Ocean | 0.30 | Enjoyable to play, adds more moods | Normal people
14 | ✔ | 2019 Storyline, weather, night mode | 10 | Time | * Adding time to game. * Either BOTW 2 min for 1 hr with longest day, or minecraft. I don't think ever step 5 minutes. * Maybe watch system * time based events, * time based characters/moving, etc. * Starting day is 12pm, day after Kipling (for 2017-2018 version). * For 2019 version make so have at least a week before kipling | 0.30 | More imersive, more well thought | LARPers, RPG players
15 | X | Online | 6 | Encrypted Save Files | * Making so save/load and all personal game data is kept safe and unhackable * Also probably encrypted is better for online pins, etc Write to a file and encrypt it after finishing * https://www.guru99.com/reading-and-writing-files-in-python.html * https://www.youtube.com/watch?v=xSGnLPTjaXo * https://docs.python.org/2/tutorial/inputoutput.html - save structured data * Update save files so you write or so you understand pickling | 0.32? | Makes game safter to play and give info to. Also less easy to hack. | Devloper
16 | ★ |  | 6 | Auto Descriptions | * Making so surroundings of obveous areas print out. * Have lore print first and then title+search around you. | 0.30 | Less bugs, more consistency | Developer
17 | X |  | BD, 30? | Creative mode | * Can add content to game and make their own quests/stories. * Maybe unlocks when you beat the game. * Save files need to be able to recompile after adding items * Able to add items, quests, people, change descriptions, etc * Almost like scripting tools within the game * Maybe make a set of mod tools with the game? Maybe those are Excel Sheets? | 0.34? | Creative/Interactive Game | Creative Person
18 | ☺ | GUI, Text display | 15 | Better Map/Quest Navigation | * Move map to right side GUI. * Map display better * quest progress tracker, can give hints on where to go/where things are * Ingame journal or notes function. | 0.30 ? | Beginer friendly game | Beginer
19 | ☺ |  | 8 | Minigames | * Mini-gamers around area. Not made by me but implemented. * pong * chess (Mitch is always there) * tetris (Zac introduces you) * Zork * watching Ascii new hope * Classic riddles/storries (goat, chicken, fox) * Liars Dice (SP or MP) Tyler and Angus in full pirate gear, Hani is part of the wall (part of the ship part of the crew (the Die is cast and Davy Jones is there as well ) | 0.30 ? | Immersive and fun | Explorers
20 | X |  | 25 ? | Google Map Import | * Use google maps data to design exteriors/interriors for things | 0.32 | Makes game easier to design, more realistic, and easy to develop | Devlopers
21 | ★ |  | 4 | Pygame Build | Make it so game can use pygame | 0.30 | More features of eveyrthing | Devlopers
22 | ★ |  | 4 | Proper Compile/Installer | * Make so it takes files automatically * gives icon automatically * does code checks out * installer gives desktop icon * Overwriting old instal to update would be nice. | 0.30 | Easy for beginingers. Easier for devlopers to push out updates. | Beginniers and developers
23 | X | Creative Mode | 15 ? | Update Launcher | * A way to make game update automatically is with an update launcher * Only if not going online * Auto save every once and a while | 0.33 ? | Early acess, easy to follow along, easy to update and keep save files | People who like being involved w. development and feedback, like to play updates
24 | X | Time | 10 | Weather | *Adding different weather changes * debufs * envoirnment to keep up emersion * Pulling realworld weather and weather predictions from an API | 0.36 | Immersive Dynamic world | RPGers, readers
25 | ☺ | GUI, Text display | 15 ? | Ingame Settings | * In GUI window have options to save/load game, pause, volume settings, window size, text size, colour settings maybe? * These settings are saved locally to the game file | 0.30 | Full fleshed, easy to change for settings | Anyone who wants to setup perfect
26 | ✔ | 2019 Kipling Update | BD, 12? | Tutorial | * Start player in secluded area/small island to get a sense but still have tutorial * First 5 minutes set tone of the game, set expectations and colour whole experience. * 3ways to draw in (best have at least 2 of these and multiple intros) * 1. Sell you with the narrative 2. Wow you with the mechanics 3. Draw you in with the spectacle * Mystery is a great tool for hooking someone. Can also sell the world (put what is compelling in there and don't hold back) * Deliver why player would want to play the game and deliver in 1st 5 minute (don't even have to take away powers). * Shouldn't front load tutorial either. They simplified it * Start with spectacular or novel. Can throw into a story already in progress (in medius res) | 0.30 | Easy for new players old alike | A new or old player
27 | X |  | 8 | Currency | * People drop money/you can make money * Petter is a seller and you can buy Marvin the Martian thing * Can drop a little bit from cops but not too much to farm * Investing in stocks that are real and pulled from an API * Grand exchange for items | 0.36 | Immersed Economy | RPGers, economists
28 | X | Combat Update | 12 | Item and Mechanic Balance | * Attack and defense, speed doesn't do anything. * Would need to be be after combat update. * Possibly have star/some sort of indicator for bosses OR have the indicator just be how hard they can hit you/how big they are * More direct reward for exploration with something that ties back into game (like BOTW) * Having body armour Quantum relic | 0.32? | Balanced and nice to play in many parallel ways | Explorers
29 | X |  | 6 | Name Manipulation | * Do more with name including character address you by name and work with names including name infulence. | 0.32? | Immersive | RPGers
30 | X | Boss Balance | 16 | Difficulties | * Easy, Medium, Hard, Ironman verson where can't heal/carry more than you can * Maybe all with different endings * Easy-medium-Hardcore modes where you have 1. map w. quest outline (maybe a box?) - exploitable map/looking - no map 2. Enemy difficulty 3. Item outlines? 4. No eating 5. Full inventory vs expandable vs just you? * Try not to do just simple health/attack scaling. Maybe add new mechanics | 0.33? | Game for all people, returning or new | People who like a challenge
31 | X |  | 20 | Item/Player Attributes | * Items can give Flying, Electricity, crafting, survival, weight, volume stored * Water, food, and stanima for player * Being able to carry more things or have Backbacks * Including Iron man suit with Energy, craftables and consumables with energy. * Secret weird flying place/base. Secret places you can only get to by flying into upper buildings * You can fly up too far and fly out of the game | 0.36? | Lots of endgame content | Collectors/maxers
32 | X |  | 10 | Collectables and Trophies | * Keep track of all items/things collected * Steam/platinum trophies | 0.37 ? | Rewarding for going along progress, collectable | Completionists
33 | X |  | 20 | Undead/Errie Update | * Ritual gone wrong that spawns dumb undead things at night. Ritual involves turning Casion calculator into the other. * If you go to edge and press side 1000(50) times you go around to the other edge * Pressing down 420 times in a certain place sents you to hell and you fight satan, and Bezabad plays. * You can also sumon Satan to get the joint of destiny * Teachers come back to life and you can kill zombie versions of them * Can eat people after you kill them(Arther), depending on who you eat you die * Maybe involve kathulu | 0.38 | Spooky | Darkness lovers
34 | ☺ | Time | 6 | NPCs | * They move around * Have a companion * Can equip items to yourself to store for later games so they act as a companion. | 0.30 | Immersive, like people | RPGers
35 | X | Creative Mode | 12 | Teliporter | * Sling ring, teliport anywhere you know * Portal gun * Teliport anywhere you can see * Instant transmission (anything) * Zombies teliporter (where another one is but also in time) * Star Trek teliport (anywhere but only to/from consol). | 0.37? | Crazy, references | Endgame Content
36 | X | Creative Mode | 20 | Desctruction | * Building and all things are breakable/fightable/destroyable. * When things break the items/characters get put on main floor but dead, interrior destroyed * Blowing up building calls to police * attack/eat rules sign/interactactables | 0.38? | Crazy, creative | Anarchists
37 | X |  | 10 | GTA Police | * Star level where police come after you, eventually SWAT * eventually have to escape on rocket in smoke stack to go meet Elon musk on the moon | 0.35 ? | Consequences/acountability for killing | Survivalists
38 | ☺ |  | 7 | Text Display | * GUI text printer, change colour, font, style of words to highlight. | 0.30 | Beautiful, bright, contrast | People who like seeing things
39 | X |  | 10 | Scater Erik Update | * Involves lore from the skate video . You see a campus police guard pull up to talk to someone on the skateboard. "Erik the Sk8r: Hey Bill" "Bill the Mac Cop: Hey Erik, you know you can't be here right?" "Bill: Comomon man we do this every day" "Erik: Okay then, see you tomorrow!" He scates off quickly up "Bill the Mac Cop: You can't skate on campus prop... aww whatever." | 0.38? | Lots of inside references | Hollywood House
40 | X | Scater Update | 30? | Hollywood Expansion | * Hollywood Murder Mystery. All aspects and functions of hollywood * Have to fight the racoons | 0.38? | Immersive world with lots of areas | Eng Phys friends, Me
41 | X | GTA police | 20? | Philpocalpyse storyline | * Phil clones himself to make it more efficient but gets out of control * Have to fight off all ranges of Phils * Only way to kill them is to poisen cafine supply into the school * So only drunk Phil remains | 0.39? | Crazy, lots of content | Eng Phys, survalists
42 | X |  | 15? | The Areana | * Fight combatants against eachother (including different Phils). * Can also fight in it yourself to go up ranks | 0.39? | Minigame/fighting challenge | Fighters
43 | X |  | 20? | Green Lake | * You teliport to green lake, explore all the mysteries of Brendan Fallon's past and life * See update notes | 0.40? | For Myself | Me
44 | X |  | 15? | Social Media and Website | * Make facebook, twitter, website, instagram outreach and update to keep players/community involved and invite new players * Put game on steam | 0.35? | Looking to grow | People who want community/involvement
45 | X | Google Maps Import | 30 ? | 1st year Storyline and Arts/quad Expansion | * Expand Map to whole school * make a storyline containing first year eng experience and classes | 0.36? | Open to all People | Mac Eng Students
46 | X |  | 10 ? | Nazi Zombies | * Just bassically Nazi Zombies mode * Wunderwaffe DG-2 1000, 100, -10 * Chain lightning! 115 not included | 0.40? | Minigames, crazyness | Zombie Lovers
47 | X |  | 20 ? | Farming | * Real life farming times for best weapons * Every 1/20 pumpkin gives mutated Wunder pumpkin which is best headgear * Because it's better reactor it's mutated * If creating long term things need to have good, stable, encrypted save files that can be updated with version * Create element 420 in the reactor to make wonder weapons | 0.42? | Endgame/many ways to play | Megan Goodland, Farmers
48 | ★ |  | 8 | Boss balance | * Making sure all bosses are beatable without secrets so at least not frustrating for new players * See balance metrics from balance sheet * Maybe only have saving and autosaving as a developer. | 0.30 | Challenging but not punishing | People who don't mind a challenge
49 | X |  | ? | Integrate into other things | * Matlab * HFF 2020 * any other game I make | ? | My pride work shown everywhere | Someone who likes text adventures
50 | ~ |  |  | Map/Items/People/Quests | * Error checking to see if place exists before moving * Wear earphones on head * 3W text in QT * Add Nicole to EP office * Wacky items are good * 3BB PID with MSP430 * Have Brendan Fallon character with eclipse mug, rocketry t-shirt, Strainer on head?SafetyGlasses?, and iron ring (more characters) * Giving context about 3W text and also have more things tell you about phoneix and also items (More use of storyline, music, definition to people to give realism to the world) * After giving dirty needle to sharp exchange a random encounter with a person that says "You're the greatest semaritan in the world" and gives you and Uzi * Need to know that Jana has the textbook, maybe the story should say that somewhere * Not obveous that equip means to pick up * Phil says that need to be pushed more toward the Phenoix (more people you talk to, or items, tell story about the Phoneix) ** Tyler wants it to be Sandbox mode, no linear stuff, events unfold from there * Expand on the Story and the high council so they can piece everything together * See TODO list for all remaining bugs
50 | ☺ | 2019 Kipling Update | BD, 10? | Artwork/title screens | * Having a ascii art converter and font typing creator * making a cover picture * having all the pictures of stuff in game
51 | ~ |  |  | Text/Grammar/Naming | * Spelling and grammar check before release (maybe needs a text output function) * Don't except empty name * "B is back" (Zac) * "Dell, Intel Inside" * search keyword for search * When you inspect the car it says 'Ya thought these were the keys' * When you searching when nothings there "You double take and there's still nothing there" (If you search 20 times you die) * See TODO list for all remaining bugs
52 | X |  |  | Procedural Generation | Having Map/dungeons, maybe charaters, proceduraly generated
53
Want to get done before december when python 2 support ends
aaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaa
Put priorties/finish list
Fix Description List
Integrate bug/must have from feedback
Integrate TODO list
Breakdown big ones
|  |  | Compile big list |  | Finished Feature lock so all future features go marked as not in this update
Layout roadmap/plan document
Games/projects need synthergy to be more than the sum of their parts
Maybe consider doing half release with all mechanics then rest of 2019 Kipling in the (maybe 0.30.0 and 0.30.5 or just 0.30 and 0.31)