## Outline
Develement Roadmap (feedback, features, featurelocks, and roadmap)
Different from TODO list which is update specific active/reactive update bugs, features, and done so far.
This roadmap is proactive, critical and directed thinking for best future development for the game.
This is apposed to just working on spur of the moment easy and fun things when I want to
May take the form of a better list
[7 empty] | ✔ | 30 mins
2019-09-01 | [6 empty] | X | Missed
Mon | Tue | Wed | Thur | Fri | Sa | Sun | 45 | Mins total worked on
9 - | 10 - ✔ Made feature lock tab | 11 - 60 Added almost all features to list | 12 - 45 Recorded Erik+Brian Music, added music to game, worked on pygame display while reading documentation. | 13 - ✔ Started going through old TODO lists. | 14 - | 15 -
16 - | 17 - | 18 - | 19 - | 20 - | 21 - | 22 -
23 - | 24 - | 25 - | 26 - | 27 - | 28 - | 29 -
30 - | 1 - | 2 - | 3 - | 4 - | 5 - | 6 -

## Feedback
Feedback | Priority | Links | When Reported (update) | Est Implement Time (hrs) | Description (64 char max) | Details | What kind of game it makes (who) | Priorities |  | -
13 | ~ |  | 0.28 | 1 | Song doesn't play when restarts |  |  | ~ | Bug | ~
14 | ~ |  | 0.28 | 0.75 | 3rd floor thode up (only go if exists error catch) |  |  | ★ | Must Have | ↑
18 | ~ |  | 0.28 | 0.75 | UH Big Hits shirt inspect glitch |  |  | ✔ | Try, see how far | ↑↑
3 | ★ |  | 0.28 | 0.25 | Look Around (Rod) |  |  | ☺ | Nice to Have | →
5 | ★ |  | 0.28 | 0.25 | No Empty name excepted (Zac) |  |  | X | Not for this update | ↓
6 | ★ |  | 0.28 | 0.25 | "B is back" (Zac) |  |  |  |  | ←
7 | ★ |  | 0.28 | 2 | Spelling/grammer (Zac, |  |  |  |  | ★
8 | ★ |  | 0.28 | 0.25 | "Dell, Intel Inside" |  |  |  |  | ☺
10 | ★ |  | 0.28 | 0.75 | *Short word for verbs, for inv, s for stats |  |  |  |  | ✔
11 | ★ |  | 0.28 | 0.25 | Wear earphones on head |  |  |  |  | X
19 | ★ |  | 0.28 | 0.25 | "search is room, inspect is individual item"
21 | ★ |  | 0.28 | 0.25 | 3W text in QT
35 | ★ |  | 0.28 | 0.25 | Angus, Beef, Barber
36 | ★ |  | 0.28 | 0.25 | "Call me a liar"
2 | ☺ |  | 0.28 | 4 | *Keep track/quest progress bar (Rod)
12 | ☺ |  | 0.28 | 0.5 | Add Nicole to EP office
15 | ☺ |  | 0.28 | 2 | Auto save every once and a while
24 | ☺ | GUI | 0.28 | 3 | Size of window (ascii art print)
30 | ☺ |  | 0.28 | 2 | Wacky items are good
31 | ☺ | GUI | 0.28 | 2 | background/text colours
32 | ☺ |  | 0.28 | 0.5 | 3BB PID with MSP430
33 | ☺ |  | 0.28 | 1.5 | Measure Alice or Bob & they collapse
34 | ☺ |  | 0.28 | 0.5 | put DOD in game
16 | ✔ | GUI | 0.28 | 4 | Arrow keys & WASD moves
17 | ✔ |  | 0.28 | 2 | attack/eat rules sign/interactactables
4 | ✔ |  | 0.28 | 1.5 | Eat People (Arth), depending on who you eat you die
28 | ✔ | Inventory | 0.28 | 2.5 | Quest inv. Vs other inventory
1 | X |  | 0.28 | 5 | Combat (Vuk)
9 | X |  | 0.28 | 3 | Say short name to pick thing
20 | X |  | 0.28 |  | Starting difficulty hard (won't put in for 2017-2018)
22 | X |  | 0.28 |  | Directions are disorienting
23 | X |  | 0.28 | 3 | Map with items come up
25 | X |  | 0.28 |  | Combat is risky
26 | X | Combat | 0.28 | 4 | Better eating/prep.
27 | X | Money | 0.28 |  | Peter as a vendor
29 | X | Inventory | 0.28 | 4 | Back Pack
aaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaa

## Alpha 0.30 Feature Lock
Alpha 0.30 - Kipling Update - Last EPTA Update Feature Lock
Leave It or Evolve It
Feature | 0.30 Priority | Links | Est Implement Time (hrs) | Description (64 char max) | Details | When to implement(update) | What kind of game it makes | Who would play this game | Priorities |  | A-Z (best) | Z-A | Extra
1 | X | All Future, Online, Getting Devs, Multiplayer | BD, 50? | Rebuild Game Engine | Classes, object methods, how map works, commenting code. Updating to python 3. Interactables class. | B 0.31 | Consistant, less bugs, well documented, easy to develop | A developer | - | Not set yet | - | X | -
2 | ★ |  | 1.5 | PAP Unlock | Make PAP unlock when you get to end of game | 0.30 | Lots of content, adds reward for finding everything | A completitionist, pushing the limits | ~ | Bug | ~ | ✔ | ~
3 | ★ | Future expansions, dungeons, kipling, tutorial room, etc | 2 | Interriors Implement | Make a basic interrior of bsb and fully test | 0.30 | More conent, better devloped | Someone who likes to explore and find secrets, also dungeon runner | ★ | Must Have | ★ | ☺ | ↑
4 | ☺ |  | 2 | Nonsense Update | Adding your dad, Alex Jones, Arnold, Jesse Ventura, auto turrets etc | 0.30 ? | Lots of easter eggs and loor | Our friends lol | ✔ | Try, see how far | ☺ | ★ | ↑↑
5 | ☺ |  | 15 | Bio Cards | Adding explinations to all jokes and inside things to keep game relavent. Not sure if this would take away from game OR if you would only play the year you have it. Idk | 0.34 ? | Someone who likes lore | Future Eng Phys people | ☺ | Nice to Have | ✔ | ~ | →
6 | ✔ |  | BD, 10? | Experience Levels + Mobs | Adding an experience level to the game and mobs that respawn so you feel like you're progressing. Probably buffs stats and helps you beat higher level people/things. Also the respawn with golden gauntlet thanos for Paul the buss driver. | 0.30 | More RPG style and feel like you're progressing | RPGs, grindy people etc | X | Not for this update | X | - | ↓
7 | ✔ | Text printer, Colour options, Ascii art generator, rescalable content | BD, 30? | GUI | Adding map and all suplementary info to the GUI (maybe whole game?) so we can customize content. IDK. I like idea of two window system with map, player icon, pictures, etc on side. | 0.30 | Easier on eyes, customizable, well refined | RPGers |  |  |  |  | ←
8 | X | All Future | BD, 40? | Online SinglePlayer | Make game run in javascript/whatever online so you can play game online. Also has QT scoreboard so more compeditive | 0.33 ? | Easy to access and play anywhere, easy to track and expand to other people | Mobile gamers, anynonwindows/don't want to download. Basically any loose gamer. Also compeditive side online | BD = task needs to be broken down to be more specific |  |  |  | ★
9 | X | All Future Updates | BD, 40? | Online MultiPlayer | Make other players be able to interact | 0.35? | MMORPG | People who play MMOs, grindy people, compeditive, etc |  |  |  |  | ☺
10 | ✔ |  | 9 | Text Parsing/Input (fast Addressing) | Make keywords shorter, have list of items to choose from quickly, maybe accept short names? Maybe take cardinal coords. More things rather than equip. |  | Well thought out, easier to player and higher skill cap | Speedrunners, first time players, etc |  |  |  |  | ✔
11 | X |  | BD, 25? | Overhauled Combat | Make combat more turn based with actions, reactions, preps, combos, etc. Maybe some skill involved? | 0.32? | Pokemon style, some darksouls ellements, more skill based | People who like grinding, more professional gamers, etc |  |  |  |  | X
12 | ✔ |  | BD, 4+10+8+15+20? | 2019 Kipling Update | Year selector, tutorial, intro, Map/characters, storyline/quests. This is a substantial piece of work | 0.30 | A game for future Eng Phys Generations. Let's me separate last year's content and this year's content. | Eng Phys friends, Me
13 | ✔ | 2019 Intro | 10 | Music + Compile | Refine music so can transitions and have different music for different settings | 0.30 | Enjoyable to play, adds more moods | Normal people
14 | ✔ | 2019 Storyline, weather, night mode | 10 | Time | Adding time to game. Maybe watch system, time based events, time based characters/moving, etc | 0.30 | More imersive, more well thought | LARPers, RPG players
15 | X | Online | 6 | Encrypted Save Files | Making so save/load and all personal game data is kept easy. Also encrypted transfer is better. | 0.32? | Makes game safter to play and give info to. Also less easy to hack. | Devloper
16 | ★ |  | 6 | Auto Descriptions | Making so surroundings of obveous areas print out | 0.30 | Less bugs, more consistency | Developer
17 | X |  | BD, 30? | Creative mode | Can add content to game and make their own quests/stories | 0.34? | Creative/Interactive Game | Creative Person
18 | ☺ |  | 15 | Better Map/Quest Navigation | Map display better, quest tracker, can give hints on where to go/where things are | 0.30 ? | Beginer friendly game | Beginer
19 | ☺ |  | 8 | Minigames | Mini-gamers around area. Not made by me but implemented. | 0.30 ? | Immersive and fun | Explorers
20 | X |  | 25 ? | Google Map Import | Use google maps data to design exteriors/interriors for things | 0.32 | Makes game easier to design, more realistic, and easy to develop | Devlopers
21 | ★ |  | 4 | Pygame Build | Make it so game can use pygame | 0.30 | More features of eveyrthing | Devlopers
22 | ★ |  | 4 | Proper Compile/Installer | Make so it takes files automatically, gives icon automatically, does code checks, and installer gives desktop icon. Overwriting old instal to update would be nice. | 0.30 | Easy for beginingers. Easier for devlopers to push out updates. | Beginniers and developers
23 | -
24 | -
25 | -
26 | -
27 | -
28 | - | Combat Update |  | Item and Mechanic Balance | Attack and defense, speed doesn't do anything. Would need to be be after combat update. Possibly have star/some sort of indicator for bosses
29 | - |  |  | Name Manipulation | Do more with name including character address you by name and work with names including name infulence.
30 | - |  |  | Difficulties | Easy, Medium, Hard, Ironman verson where can't heal/carry more than you can.
31 | -
32 | -
33 | -
34 | -
35 | -
aaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaa
Want to get done before december when python 2 support ends