## Outline
Develement Roadmap (feedback, features, featurelocks, and roadmap)
Different from TODO list which is update specific active/reactive update bugs, features, and done so far.
This roadmap is proactive, critical and directed thinking for best future development for the game.
This is apposed to just working on spur of the moment easy and fun things when I want to
May take the form of a better list
ONCE this is done no more large features can be added
[8 empty] | ✔ | 30 mins
2019-09-01 | [7 empty] | X | Missed
Mon | Tue | Wed | Thur | Fri | Sa | Sun | Total | 45 | Mins total worked on
9 - | 10 - ✔ Made feature lock tab | 11 - 60 Added almost all features to list | 12 - 45 Recorded Erik+Brian Music, added music to game, worked on pygame display while reading documentation. | 13 - ✔ Started going through old TODO lists. | 14 - 45 going through lists, still need to go through written work then clean up the actual list before priority and breaking down big ones. | 15 - 120 Attempted to make game playable by changing sound effects, realized will be unplayble until inbetween build, layed game without secrets to look for feedback and balance (file called Doug for Alpha0.29, made file in balance folder, Added last things from google keep notes | 330 min/5.5 hr | 1 hr | Hours total worked on
16 - X | 17 - 45 finished feature lock list, needs descr. Cleanup, feedback, and review | 18 - 90 Cleaned up features list, started going through and combining with feedback | 19 - ✔ Finished integrating feedback and integrating TODO list | 20 - ✔ Integrated TODO list and EBTA Written work, ready for breakdown | 21 - ✔ Started whiteboarding list. Next will be writing up list and actually breaking things down into tasks. | 22 - ✔ breaking down auto descriptions on whiteboard | 195 min/3.25 hr | Would like to finish feature lock at least and get into breakdown
23 - ✔ breaking doen GUI on whiteboard and still needs work | 24 - 1 hr GUI on whiteboard coming up with schemes | 25 - ✔ rethinking GUI layout on whiteboard, rethinking entire GUI and input architecture of the game (eg. if text based adventure would focus on terminal/text parser but because MUD want to focus on integrated and fully easy to use GUI. Game will start default Consol mode but support WASD w. hotkeys and possibly controller support) | 26 - ✔ Transferred List and did macro schedule. Shits bad | 27 - 1.25 hr remade list and populating for breakdown tomorrow | 28 -1.75 gr breaking down Boss balance, adding update features, getting milestones for scheduling | 29 - ✔ organized some of the lists | 360 min/6 hr | Get through 0.30.0 Breakdown
30 - 1.5 hr Started breaking down some things but then got into the rabit hole of natural language processing leading to the note I now have. I learned about IL (Interactive Literature) community which is bassically text based adventures and how I can pull on them for help and creations. | OCT 1 - 1.5 hr searching through different text parsers/developers and whiteboarding | 2 - 3.5 hr Searching through IF packages/called authoring systems. Found Python and Non-python ones. Needs lots of time for this investigation. | 3 - X | 4 - 1.5 hr whiteboarding, reading IF authoring, disscussing in my Car. | 5 - 1.75 hrs writing parser file outline, parser research+reading, and whiteboarding out parser implementation | 6 - X | 585 min/9.75 hr | Feature lock, breakdown, plan, and shechedule by Oct 7th
7 - 3 hrs Alpha 0.30.0 Breaking down, integrating Notes, limits, detailed, ACTUAL FEATURE LOCK AND SCHEUDULE! Time to start! | 8 -X | 9 - 1.5 hrs removing music/sound, info, stats, and setting up dev keywords | 10 - 2.5 Going through dev mode settings, discovering CLEAR SCREEN AND COLOURS CAN BE A THING | 11 - Next is trying renaming files for obsurity, windows file hiding, command creative mode, and looking more/defining more | 12 - | 13 - |  | Finish 0.30.0 Feature Lock+Plan+Schedule. Start Developing and Learning PyGame
14 - | 15 - | 16 - | 17 - | 18 - | 19 - | 20 -
21 - | 22 - | 23 - | 24 - | 25 - | 26 - | 27 -
28 - | 29 - | 30 - | 31 - | NOV 1 - | 2 - | 3 -
4 - | 5 - | 6 - | 7 - | 8 - | 9 - | 10 -
11 - | 12 - | 13 - | 14 - | 15 - | 16 - | 17 -
Pygame Learning
Oct 7 - | 8 - | 9 - ✔ Learning framework display and events | 10 - ✔ Learned colouring, rectangles, some key events, and basic framework of moving objects | 11 - | 12 - | 13 - |  | ✔ | 1 hr
14 - | 15 - | 16 - | 17 - | 18 - | 19 - | 20 - |  | X | Missed
21 - | 22 - | 23 - | 24 - | 25 - | 26 - | 27 - |  | 45 | Mins total worked on
28 - | 29 - | 30 - | 31 - | NOV 1 - | 2 - | 3 - |  | 1 hr | Hours total worked on
4 - | 5 - | 6 - | 7 - | 8 - | 9 - | 10 -
11 - | 12 - | 13 - | 14 - | 15 - | 16 - | 17 - | I like this structure of learning/looking through next thing while working on the thing before!
Might be able to keep up through INFORM, Zombie Modding, and Unity
Constantly need to find a good learning source though

## Feedback
Feedback | Priority | Links | When Reported (update) | Est Implement Time (hrs) | Description (64 char max) | Details | What kind of game it makes (who) | Priorities |  | -
13 | ~ |  | 0.28 | 1 | Song doesn't play when restarts |  |  | - | Not set yet | ~
14 | ~ |  | 0.28 | 0.75 | 3rd floor thode up (only go if exists error catch) |  |  | ~ | Bug | ↑
18 | ~ |  | 0.28 | 0.75 | UH Big Hits shirt inspect glitch |  |  | ★ | Must Have | ↑↑
3 | ★ |  | 0.28 | 0.25 | Look Around (Rod) |  |  | ✔ | Try, see how far | →
5 | ★ |  | 0.28 | 0.25 | No Empty name excepted (Zac) |  |  | ☺ | Nice to Have | ↓
6 | ★ |  | 0.28 | 0.25 | "B is back" (Zac) |  |  | X | Not for this update | ←
7 | ★ |  | 0.28 | 2 | Spelling/grammer (Zac, |  |  |  |  | ★
8 | ★ |  | 0.28 | 0.25 | "Dell, Intel Inside" |  |  |  |  | ☺
10 | ★ |  | 0.28 | 0.75 | Short word for verbs, for inv, s for stats |  |  |  |  | ✔
11 | ★ |  | 0.28 | 0.25 | Wear earphones on head |  |  |  |  | X
19 | ★ |  | 0.28 | 0.25 | "search is room, inspect is individual item"
21 | ★ |  | 0.28 | 0.25 | 3W text in QT
35 | ★ |  | 0.28 | 0.25 | Angus, Beef, Barber ("Call me a liar")
43 | ★ | Music | 0.28 | 0.5 | Belzabad plays when you fight kleiman
46 | ★ |  | 0.28 | 1.5 | Fix all text problems or make more auto text mechanics to improve playability
48 | ★ |  | 0.29 | 0.5 | Have Brendan Fallon character with eclipse mug, rocketry t-shirt, Strainer on head?SafetyGlasses?, and iron ring (more characters)
2 | ☺ |  | 0.28 | 4 | *Keep track/quest progress bar (Rod)
12 | ☺ |  | 0.28 | 0.5 | Add Nicole to EP office
15 | ☺ |  | 0.28 | 2 | Auto save every once and a while | I kinda disagree with this one for now. Don't think it should autosave
24 | ☺ | GUI | 0.28 | 3 | Size of window (ascii art print)
30 | ☺ |  | 0.28 | 2 | Wacky items are good
31 | ☺ | GUI | 0.28 | 2 | background/text colours
32 | ☺ |  | 0.28 | 0.5 | 3BB PID with MSP430
33 | ☺ |  | 0.28 | 1.5 | Measure Alice or Bob & they collapse
34 | ☺ |  | 0.28 | 0.5 | put DOD in game
36 | ☺ | Balance | 0.29 | 6 | Balance | * Right now defense is v important but with healing items added this should fix it * Better head items plz * Need story arc for body armour
38 | ☺ |  | 0.28 | 1.5 | Text | * When you inspect the car it says 'Ya thought these were the keys' * When you searching when nothings there "You double take and there's still nothing there" (If you search 20 times you die)
40 | ☺ |  | 0.28 | 5 | More use of storyline, music, definition to people to give realism to the world
42 | ☺ |  | 0.27 | 0.5 | SharpExchange | After giving dirty needle to sharp exchange a random encounter with a person that says "You're the greatest semaritan in the world" and gives you and Uzi
44 | ☺ |  | 0.28 | 2 | Expand on the Story and the high council so they can piece everything together
45 | ☺ |  | 0.28 | 3 | Put item descriptions to have items help tell the story
4 | ✔ |  | 0.28 | 1.5 | Eat People (Arth), depending on who you eat you die
16 | ✔ | GUI | 0.28 | 4 | Arrow keys & WASD moves
17 | ✔ |  | 0.28 | 2 | attack/eat rules sign/interactactables
28 | ✔ | Inventory | 0.28 | 2.5 | Quest inv. Vs other inventory
37 | ✔ |  | 0.28 | 2 | Queues | * Need to know that Jana has the textbook, maybe the story should say that somewhere * Not obveous that equip means to pick up * Phil says that need to be pushed more toward the Phenoix (more people you talk to, or items, tell story about the Phoneix)
47 | ✔ |  | 0.28 | ? | Tyler wants it to be Sandbox mode, no linear stuff, events unfold from there
50 | X |  | 0.29 | 4 | Easier way to access game, not just goo.gl/iK8dL9 (Website maybe)
1 | X |  | 0.28 | 5 | Combat (Vuk)
9 | X |  | 0.28 | 3 | Say short name to pick thing
20 | X |  | 0.28 |  | Starting difficulty hard (won't put in for 2017-2018)
22 | X |  | 0.28 |  | Directions are disorienting
23 | X |  | 0.28 | 3 | Map with items come up
25 | X |  | 0.28 |  | Combat is risky
26 | X | Combat | 0.28 | 4 | Better eating/prep.
27 | X | Money | 0.28 |  | Peter as a vendor
29 | X | Inventory | 0.28 | 4 | Back Pack
39 | X |  | 0.28 | 3 | Notes option (a list of all lore you've gone through)
41 | X |  | 0.28 | 5 | Some sort of skill component to fighting
49 | X |  | 0.28 | ? | AR version of the game -Ekamada
Put into feature lock |  |  |  |  | aaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaa

## Alpha 0.30 Feature Lock
Alpha 0.30 - Kipling Update - Last EPTA Update Feature Lock
Leave It or Evolve It
More details may be broken down in Whiteboard pictures but not going to copy
Feature | 0.30 Priority | Links | Est Implement Time (hrs) | Description (64 char max) | Details | When to implement(update) | What kind of game it makes | Who would play this game | Priorities |  | A-Z (best) | Z-A | Extra
1 | 4. X | All Future, Online, Getting Devs, Multiplayer | BD, 50? | Rebuild Game Engine | * Classes, object methods, how map works (numbered adjacency lists), commenting code. Updating to python 3. Interactables class. Buildings as an entity. * PP8 style using PyCharm * Get rid of global variables and restructure code * Maybe make each class and big function its own module file * Using and understanding effecient python code chunks (See Liam F. and his book) * Make an entity class (name, description, location, stats, health, item need, item give, inventory, deathtext, etc) and then all subclasses using inheritance * Map So we are making a MUD and I didn't know it LOL Better than trying to retrofit everything and then you have unique addressing Have a linked exit on the spots beside, no need to go inside or anything, just update position and move around Map will just constrain itself by where edges are and where you can move * Nevada Game engine Graph with adjacency list (stored effeciently) that gives the possible options. Using paths with path constructor to translate between points (instead of on-command search). Then maps just become entities addresses by the name. For destruction just do pointer to point all old places to the new place (but does damage/kill people when you do destroy a spot) * Entity Person(each has same attributes and stuff, even schedule would be the same) Boss? Place Interroor Item Interactable Interactable can go, just add a moveable flag to items with new entity structute that allows give/take * Have a generalized interface class/objects so you don't have to make new ones every time * Calling it Mac Quest? McMaster MUD? MMUD * See TODO list for rest of rebuild notes | B 0.31 | Consistant, less bugs, well documented, easy to develop | A developer | -1. - | Not set yet | - | X | -
2 | 1. ★ |  | 1.5 | PAP Unlock | * Make PAP unlock when you get to end of game * Unlocked by finishing all of the game * Sound of lightening * followed by the sounds of cowboys * Looks like you need to give something to get something in return * PAP EXP level * - [x] Pack-a-punch - [ ] With sounds when it starts and ends - [ ] Bell dongs every hour | 0.30.9 | Lots of content, adds reward for finding everything | A completitionist, pushing the limits | 0. ~ | Bug | ~ | ✔ | ~
3 | 1. ★ | Future expansions, dungeons, kipling, tutorial room, etc | 2 | Interriors Implement | * Make a basic interrior of bsb and fully test. * Then make all multilevel buildings an interrior * Shouldn't be in here but also from load screen Allow you to save as/copy, and delete files * Dictionary with dimension number so you only need to reference that | 0.30.9 | More conent, better devloped | Someone who likes to explore and find secrets, also dungeon runner | 1. ★ | Must Have | ★ | ☺ | ↑
4 | 3. ☺ |  | 2 | Nonsense/Insanity Update | * Adding your dad, Alex Jones, Arnold, Jesse Ventura, auto turrets etc, harry potter ring that can talk to the dead * Even more secret place under okons storage place. Leads to underground base. * Mike the liar random event. Running across campus saying stuff. Comments on 4th wall things about the game ex) "They need an autocomplete" * Stackable Visor Glasses * Brendan's jacket holds things in the game * scuba Steve (and it's Haugen) * Make EpiPen able to save you * Big Lez show intercut 00:38:40, 00:49:00 * Revive life by having a fairy * Insanity Update ADDED Your dad and Super crocs that show secrets Alex Jones Rhomes around Brings you down to 1 health unless you have a tin foil hat Super Male Vitality -5, -5, -5, -5 has been used by Alex Jones in order to maximize vitality when working up to 12 hours a day or more in the fight for freedom. Patriot Blend Medium Roast -5,-5,15, 5 Start your day off right with our gourmet, 100% organic coffee and help us Wake Up America! Jesse Ventura I'm a peaceful warrior I HUNTED PREDITORS IN QUATAMALA. I DON"T HAVE TO DO ANYTHING. WHAT ARE YOU MY COMMANDING OFFICER | 0.30.9 | Lots of easter eggs and loor | Our friends lol | 2. ✔ | Try, see how far | ☺ | ★ | ↑↑
5 | 3. ☺ |  | 20 | Bio Cards | * Adding explinations to all jokes and inside things to keep game relavent. Not sure if this would take away from game OR if you would only play the year you have it. Idk. * When characters die they drop bio cheet and what their interests are (credits like a great help for devloping game) (44 ENEMIES, short to long biosheet) 8.0 Writing (Tyler and Mitch's Help) 5.0 Need some sort of ENEMY Attribute that you can fill that text with and they drop an item that's created with that biosheet. Or make the items one by one and there's a new special drop section * Add better description of items/Interacts/Talking text to explain jokes, point to clues, and more help to have players finish the game and enjoy it (148 items, 27 interacts) 3.0 Playthrow game strategically as though don't know ANYTHING about ENG PHYS or McMaster (maybe this isn't what we want but I'll talk to Tyler/Mitch) and see how far I would get what's going on and get content to write 4.0 Make and adjust titles | 0.30.0 | Someone who likes lore | Future Eng Phys people | 3. ☺ | Nice to Have | ✔ | ~ | →
6 | 2. ✔ |  | BD, 20? | Experience Levels + Mobs | * Adding an experience level to the game and mobs that respawn so you feel like you're progressing. Probably buffs stats and helps you beat higher level people/things. Also the respawn with golden gauntlet thanos for Paul the buss driver. * have SOME sort of leveling/experience system (weapons or yourself) Overall level based on exponential EXP and experience gained on Enemy health or quests Cows in OSRS respawn based on player count, I'll do random from 0.5-2 mins based on stats/level? * In general, have more crazy/dangerous things happen as you progress in quests/storyline (sand worms pop up, idk, crazyness) * Could have random drop loot * Having fire with cooking be able to cook multiple types of foods (Eggs, meat, bread, ) with BOTW sound * Having more combinations of cooking food * Having more Runescape cooking, experience levels to unlock/burn less, burn levels, etc * Make a really hard boss that is almost impossible to beat (Single High combat class mob or boss for challenge) * Talking experience to level up by talking to NPCs (just talk faster? Unlocks the quest? Will say "OKAY OKAY I"LL GIVE YOU WHATEVER YOU WANT") | 0.30.9 | More RPG style and feel like you're progressing | RPGs, grindy people etc | 4. X | Not for this update | X | - | ↓
7 | 2. ✔ | Text printer, Colour options, Ascii art generator, rescalable content | BD, 30? | GUI | * Adding map and all suplementary info to the GUI (maybe whole game?) so we can customize content. * IDK. I like idea of two window system with map, player icon, pictures, etc on side. * Size of window (ascii art print) ** All ellements possible are text based * Health/other indicators like blood on screen instead of just health bar * Every time you launch different load screen background, text colour, font (as long as it looks good) as well as being able to choose * Starting screen is on GUI and then there's a try me section with a Consol and 'mini' tutorial where you're stuck in a white room with red chair and radio TV * * Have the indicator just be how hard they can hit you/how big they are * Option to be left handed and show items in left hand | 0.30.9 | Easier on eyes, customizable, well refined | RPGers |  |  |  |  | ←
8 | 4. X | All Future | BD, 40? | Online SinglePlayer | * Make game run in javascript/whatever online so you can play game online. * Also has QT scoreboard so more compeditive | 0.33 ? | Easy to access and play anywhere, easy to track and expand to other people | Mobile gamers, anynonwindows/don't want to download. Basically any loose gamer. Also compeditive side online | BD = task needs to be broken down to be more specific |  |  |  | ★
9 | 4. X | All Future Updates | BD, 40? | Online MultiPlayer | * Make other players be able to interact, fight, talk to eachother | 0.35? | MMORPG | People who play MMOs, grindy people, compeditive, etc |  |  |  |  | ☺
10 | 2. ✔ |  | 9 | Input (fast Addressing) | *-fast addressing like underlining the shortcut, having one letter verrbs, and having be able to pick up things using the number position it was displayed it (maybe display number?). Then can type like "p 1" to pick up first item. Also maybe can do multiple notations like "p 3-6" or "p 3,5,6" or "exa 1,3". Also make sure the items display in order they were in * Make keywords shorter, have list of items to choose from quickly [1-2], maybe accept short names? * Maybe take cardinal coords. * More things rather than equip. * Also possibly controller support? * Short word for verbs, for inv, s for stats * Try having WASD and other key accepts (maybe arrow keys) on the GUI acceptable * add verb accepts for 2 words and 1 word for * add accept for remove, speak, look * move, go, run, jog, bike, scate, drive, head * add cardinal directions to those directions * See if accept accents and other characters in output/input. * Have a whole user input module that deciphers input | 0.30.9 | Well thought out, easier to player and higher skill cap | Speedrunners, first time players, etc |  |  |  |  | ✔
11 | 4. X |  | BD, 25? | Overhauled Combat | * See 13 Hollywood Productions March 7th large section of ideas. * Make combat more turn based with actions, reactions, preps, combos, etc. * Maybe some skill involved? * Mashing a key to beat someone. * At least for now someone comes back for round two. * Every Person has their own weakness/strengths. * Use Darksouls style damage system (non-subtractive) * Bullet time * Maybe have speed play more of a factor, maybe balance in other ways * Name everything and attack dialougs (use x to do y) * High skill cap mobs you need to farm * -more health near end of health bar -first bit of damage doesn't actually hurt you a lot -hud elements, no health bar just visual indicators -all GUI things in dead space are immersed in the game * Left and right hand dominance/experience | 0.32? | Pokemon style, some darksouls ellements, more skill based | People who like grinding, more professional gamers, etc |  |  |  |  | X
12 | 2. ✔ |  | BD, 15+8+15+20+30? | 2019 Kipling Update | *Year selector * intro * Map/characters ( Measure Alice or Bob & they collapse, also DOD) * BSB Dungeon * storyline/quests. This is a substantial piece of work See EBTA Writing on Keep * See Google Keep notes on the story * tutorial * BSB IS A DUNGEON WITH KEYS (EITHER UNIQUE OR NOT ) * Have Brendan Fallon character with eclipse mug, rocketry t-shirt, Strainer on head?SafetyGlasses?, and iron ring (more characters) * Find Jameson who was sick and get solutions to his bot * Make something to wake up Liam Dow * Go to find Steven but he's not there or in the carabean * More direct reward for exploration with something that ties back into game (like BOTW) | 0.30.9 | A game for future Eng Phys Generations. Let's me separate last year's content and this year's content. | Eng Phys friends, Me
13 | 2. ✔ | 2019 Intro | 10 | Music + Compile | * Allow Sounds to play * transitions and have * different music for different * * Belzabad plays when you fight kleiman * Channel Orange by Frank Ocean * More/changing voice dialoges for people * ability for characters to play audio when you talk to them * Make high pitch willhelm screen when women die * High energy section of: Neverland by prismo * Grand Canyon by Kavinsky * Learn to fly without wings -Vulpek | 0.30.9 | Enjoyable to play, adds more moods | Normal people
14 | 2. ✔ | 2019 Storyline, weather, night mode | 10 | Time | * Adding time to game. * Either BOTW 2 min for 1 hr with longest day, or minecraft. I don't think ever step 5 minutes. * In BOTW 2m = 1 hr and very long days. How much in Minecraft? * Maybe watch system * time based events, * time based characters/moving, etc. * Starting day is 12pm, day after Kipling (for 2017-2018 version). * For 2019 version make so have at least a week before kipling | 0.30.9 | More imersive, more well thought | LARPers, RPG players
15 | 4. X | Online | 6 | Encrypted Save Files | * Making so save/load and all personal game data is kept safe and unhackable * Also probably encrypted is better for online pins, etc Write to a file and encrypt it after finishing * https://www.guru99.com/reading-and-writing-files-in-python.html * https://www.youtube.com/watch?v=xSGnLPTjaXo * https://docs.python.org/2/tutorial/inputoutput.html - save structured data * Update save files so you write or so you understand pickling * change the file extensions and names of folders in EBTA to .EBTA or something random (or blank) to hide or obscure files (make sure it works) | 0.32? | Makes game safter to play and give info to. Also less easy to hack. | Devloper
16 | 1. ★ |  | 8 | Auto Descriptions | * Making so surroundings of obveous areas print out. * Have lore print first and then title+search around you. | 0.30.0 | Less bugs, more consistency | Developer
17 | 4. X | Mod Tools | BD, 30? | Creative mode | * Can add content to game and make their own quests/stories. * Maybe unlocks when you beat the game. * Save files need to be able to recompile after adding items * Able to add items, quests, people, change descriptions, etc * Almost like scripting tools within the game | 0.34? | Creative/Interactive Game | Creative Person
18 | 3. ☺ | GUI, Text display | 20 | Quest Navigation | * quest progress tracker, can give hints on where to go/where things are * Ingame journal or notes function. * Notebook where you write each questline/tutorial * has quests, notes, item/interact tracker, people tracker, map, settings * Quests tracks each main and sidequest line 3.0 will be updated each talk/advancement (will need a flag/checker 6.0 Needs a list interface that you can flip back through pages and go to next one * 5.0 Notes is a similar interface but can write and type in each line Lines are fixed and specified by number, bassically a big list (print out using printT) Writing to a line overwrites whole line * 3.0 list of items and their location (with name), also people * 1.5 Map is minimap, settings is setting screen * 1.0 whenever you do something 'noteworthy' it says you take a note, also when you open the book is says "You open your ___ (maticulously empty, nearly full, etc for completion) notebook" Wordy Version from Keep *Have Journal be your quest notes, your own notes, settings, map, and tutorial notes Journal should write down important things based on the previous quests flags and based on talking (e.g. when you find Lapierre and speak to him, it writes down what you wants based off of speak trigger. Once you complete his quests it writes it down based off of the quest trigger. For updated Sinfo like Minnick would need to update in the questline Seperated by questline Main quests and side quests, maybe won't be obvious that it's the main quest at first? Nawww let's have it clear what the main quest is. | 0.30.0 if not 0.30.9 or later | Beginer friendly game | Beginer
19 | 3. ☺ |  | 8 | Minigames | * Mini-gamers around area. Not made by me but implemented. * pong * chess (Mitch is always there) * tetris (Zac introduces you) * Zork * watching Ascii new hope * Classic riddles/storries (goat, chicken, fox) * Liars Dice (SP or MP) Tyler and Angus in full pirate gear, Hani is part of the wall (part of the ship part of the crew (the Die is cast and Davy Jones is there as well ) | 0.30.9 | Immersive and fun | Explorers
20 | 4. X |  | 25 ? | Google Map Import | * Use google maps data to design exteriors/interriors for things | 0.32 | Makes game easier to design, more realistic, and easy to develop | Devlopers
21 | 1. ★ |  | 4 | Pygame Build | Make it so game can use pygame | 0.30.0 | More features of eveyrthing | Devlopers
22 | 1. ★ |  | 7 | Proper Compile/Installer | * Make so it takes files automatically * gives icon automatically * does code checks out * installer gives desktop icon * Overwriting old instal to update would be nice. * Try changing the file extensions and names of folders in EBTA to .EBTA or something random (or blank) to hide or obscure files (make sure it works first) | 0.30.0 | Easy for beginingers. Easier for devlopers to push out updates. | Beginniers and developers
23 | 4. X | Creative Mode | 15 ? | Update Launcher | * A way to make game update automatically is with an update launcher * Only if not going online * Auto save every once and a while | 0.33 ? | Early acess, easy to follow along, easy to update and keep save files | People who like being involved w. development and feedback, like to play updates
24 | 4. X | Time | 10 | Weather | *Adding different weather changes * debufs * envoirnment to keep up emersion * Pulling realworld weather and weather predictions from an API | 0.36 | Immersive Dynamic world | RPGers, readers
25 | 3. ☺ | GUI, Text display | 10 | Ingame Settings | * In GUI window have options to save/load game, pause, text speed, volume settings, window size, text size, colour settings maybe? * These settings are saved locally to the game file * For 0.30.0 3.0 Make an interface that is in game and also at the start Have it just extend the gamesettings dictionary and implement with: 1.0 pause (pauses game time), 5.0 window size that shows print limits in both directions (x and y) (affects ascii art, gives suggestion on console size and lets you increase or decrease text per line for printer), If you have this will have to have a min window size for some fixed displays 1.0 feedback (link), disclaimer (same one), credits (same as ending) | 0.30.0 | Full fleshed, easy to change for settings | Anyone who wants to setup perfect
26 | 2. ✔ | 2019 Kipling Update | BD, 12? | Tutorial | * Start player in secluded area/small island to get a sense but still have tutorial * First 5 minutes set tone of the game, set expectations and colour whole experience. * 3ways to draw in (best have at least 2 of these and multiple intros) * 1. Sell you with the narrative 2. Wow you with the mechanics 3. Draw you in with the spectacle * Mystery is a great tool for hooking someone. Can also sell the world (put what is compelling in there and don't hold back) * Deliver why player would want to play the game and deliver in 1st 5 minute (don't even have to take away powers). * Shouldn't front load tutorial either. They simplified it * Start with spectacular or novel. Can throw into a story already in progress (in medius res) | 0.30.9 | Easy for new players old alike | A new or old player
27 | 4. X |  | 8 | Currency | * People drop money/you can make money * Petter is a seller and you can buy Marvin the Martian thing * Can drop a little bit from cops but not too much to farm * Investing in stocks that are real and pulled from an API * Grand exchange for items | 0.36 | Immersed Economy | RPGers, economists
28 | 3. ☺ | Combat Update | 19-20 | Item, story, Mechanic Balance/Expan | * See what the item meta is based on the combat. 1.5 Analyizing combat and seeing what items are favoured based on calculations 0.5 Make sure no items are broken based on this 1.0 Make sure all items in game work with way you might discover them at time you would (playthrough with item to fight people) 2.0 If anything is broken fix the numbers. Making sure Attack,defense, and speed balance ( Make sure all items favour equally for game) because right now doesn't do anything. * Having body armour Quantum relic 0.5 Story ideas 4.0 Story (Item+prof+quest creation) writing 1.0 Checking story works and nothing is broken (playthrough) 1.0 Fixing anything Maybe some sort of weird sidequest that still is relavant to that year, maybe involving sharpXChange Give the Needle, someone says you're the greatest semaritan, he gives you a package it's an uzi, you can use it or turn it into the authorities They give you bulletproof vest for your crime fighting deeds ^This isn't really eng phys related enough, ask Tyler Maybe Interdisiplinary Route where you get Nuclear+Solar+Laser Powered Battle Suit It starts with Cam Churchil and the Society program? Idk * 1.0 Switch around storyline profs. nice to have: switch Kitai and Knights from optics to nano, have Lapierre and Kleinman in optics? I really don't know, they all do semiconductors with light but Kitai is definitely Nano and if he switches it can be with Kleinman at least Maybe add Bradly in there next to knights | 0.30.0 | Balanced and nice to play in many parallel ways | Explorers
29 | 4. X |  | 6 | Name Manipulation | * Do more with name including character address you by name and work with names including name infulence. | 0.32? | Immersive | RPGers
30 | 4. X | Boss Balance | 16 | Difficulties | * Easy, Medium, Hard, Ironman verson where can't heal/carry more than you can * Maybe all with different endings * Easy-medium-Hardcore modes where you have 1. map w. quest outline (maybe a box?) - exploitable map/looking - no map 2. Enemy difficulty 3. Item outlines? 4. No eating 5. Full inventory vs expandable vs just you? * Try not to do just simple health/attack scaling. Maybe add new mechanics | 0.33? | Game for all people, returning or new | People who like a challenge
31 | 4. X |  | 20 | Item/Player Attributes | * Items can give Flying, Electricity, crafting, survival, weight, volume stored * Water, food, and stanima for player * Being able to carry more things or have Backbacks * Including Iron man suit with Energy, craftables and consumables with energy. * Secret weird flying place/base. Secret places you can only get to by flying into upper buildings * You can fly up too far and fly out of the game | 0.36? | Lots of endgame content | Collectors/maxers
32 | 4. X |  | 10 | Collectables and Trophies | * Keep track of all items/things collected * will need to Keep lots of stats on character including dumb ones like people killed, items picked up, spaces/distance moved, etc * Steam/platinum trophies | 0.37 ? | Rewarding for going along progress, collectable | Completionists
33 | 4. X |  | 20 | Undead/Errie Update | * Ritual gone wrong that spawns dumb undead things at night. Ritual involves turning Casion calculator into the other. * If you go to edge and press side 1000(50) times you go around to the other edge * Pressing down 420 times in a certain place sents you to hell and you fight satan, and Bezabad plays. * You can also sumon Satan to get the joint of destiny * Teachers come back to life and you can kill zombie versions of them * Can eat people after you kill them(Arther), depending on who you eat you die * Maybe involve kathulu | 0.38 | Spooky | Darkness lovers
34 | 3. ☺ | Time | 6 | NPCs | * They move around * Have a companion * Can equip items to yourself to store for later games so they act as a companion. * Playable Characters where you can actually choose one of the players in the game and play as them (but unlock them as you go through story, do their quests, etc) like playable characters in Lego Games | 0.30.9 | Immersive, like people | RPGers
35 | 4. X | Creative Mode | 12 | Teliporter | * Sling ring, teliport anywhere you know * Portal gun * Teliport anywhere you can see * Instant transmission (anything) * Zombies teliporter (where another one is but also in time) * Star Trek teliport (anywhere but only to/from consol). | 0.37? | Crazy, references | Endgame Content
36 | 4. X | Creative Mode | 20 | Desctruction | * Building and all things are breakable/fightable/destroyable. * When things break the items/characters get put on main floor but dead, interrior destroyed * Blowing up building calls to police * attack/eat rules sign/interactactables | 0.38? | Crazy, creative | Anarchists
37 | 4. X |  | 10 | GTA Police | * Star level where police come after you, eventually SWAT * eventually have to escape on rocket in smoke stack to go meet Elon musk on the moon | 0.35 ? | Consequences/acountability for killing | Survivalists
38 | 3. ☺ | GUI | 7 | Text Display on GUI | * GUI text printer/input, change colour, font, style of words to highlight. | 0.30.9 | Beautiful, bright, contrast | People who like seeing things
39 | 4. X |  | 10 | Scater Erik Update | * Involves lore from the skate video . You see a campus police guard pull up to talk to someone on the skateboard. "Erik the Sk8r: Hey Bill" "Bill the Mac Cop: Hey Erik, you know you can't be here right?" "Bill: Comomon man we do this every day" "Erik: Okay then, see you tomorrow!" He scates off quickly up "Bill the Mac Cop: You can't skate on campus prop... aww whatever." | 0.38? | Lots of inside references | Hollywood House
40 | 4. X | Scater Update | 30? | Hollywood Expansion | * Hollywood Murder Mystery. All aspects and functions of hollywood * Have to fight the racoons | 0.38? | Immersive world with lots of areas | Eng Phys friends, Me
41 | 4. X | GTA police | 20? | Philpocalpyse storyline | * Phil clones himself to make it more efficient but gets out of control * Have to fight off all ranges of Phils * Only way to kill them is to poisen cafine supply into the school * So only drunk Phil remains | 0.39? | Crazy, lots of content | Eng Phys, survalists
42 | 4. X |  | 15? | The Areana | * Fight combatants against eachother (including different Phils). * Can also fight in it yourself to go up ranks | 0.39? | Minigame/fighting challenge | Fighters
43 | 4. X |  | 20? | Green Lake | * You teliport to green lake, explore all the mysteries of Brendan Fallon's past and life * See update notes | 0.40? | For Myself | Me
44 | 4. X |  | 15? | Social Media and Website | * Make facebook, twitter, website, instagram outreach and update to keep players/community involved and invite new players * Put game on steam *If you put it online have Wix website link (with small link to that and direct link to play online) Even if you don't online maybe you can place for downloads *Nice to Have archive versions of the game up | 0.35? | Looking to grow | People who want community/involvement
45 | 4. X | Google Maps Import | 30 ? | 1st year Storyline and Arts/quad Expansion | * Expand Map to whole school * make a storyline containing first year eng experience and classes | 0.36? | Open to all People | Mac Eng Students
46 | 4. X |  | 10 ? | Nazi Zombies | * Just bassically Nazi Zombies mode * Wunderwaffe DG-2 1000, 100, -10 * Chain lightning! 115 not included | 0.40? | Minigames, crazyness | Zombie Lovers
47 | 4. X |  | 20 ? | Farming | * Real life farming times for best weapons * Every 1/20 pumpkin gives mutated Wunder pumpkin which is best headgear * Because it's better reactor it's mutated * If creating long term things need to have good, stable, encrypted save files that can be updated with version * Create element 420 in the reactor to make wonder weapons | 0.42? | Endgame/many ways to play | Megan Goodland, Farmers
48 | 1. ★ |  | 10-18, 20 | Boss balance | * Making sure all bosses are beatable without secrets so at least not frustrating for new players * See balance metrics from balance sheet * More exploration as a player * maybe add slowww healing factor | 0.30.0 | Challenging but not punishing | People who don't mind a challenge
49 | 4. X |  | ? | Integrate into other things | * Convert the game to Matlab to play! * HFF 2020 * any other game I make | 0.43 | My pride work shown everywhere | Someone who likes text adventures
50 | 0. ~ |  | 5 | Map/Items/People/Quests/ known Bugs | * Error checking to see if place exists before moving * Wear earphones on head * 3W text in QT * Add Nicole to EP office * Wacky items are good * 3BB PID with MSP430 * Giving context about 3W text and also have more things tell you about phoneix and also items (More use of storyline, music, definition to people to give realism to the world) * After giving dirty needle to sharp exchange a random encounter with a person that says "You're the greatest semaritan in the world" and gives you and Uzi * Need to know that Jana has the textbook, maybe the story should say that somewhere * Not obveous that equip means to pick up * Phil says that need to be pushed more toward the Phenoix (more people you talk to, or items, tell story about the Phoneix) ** Tyler wants it to be Sandbox mode, no linear stuff, events unfold from there * Expand on the Story and the high council so they can piece everything together * See TODO list for all remaining bugs | 0.30.0
50 | 3. ☺ | 2019 Kipling Update, GUI | 7 | Scaling Art + Artwork | * Having a ascii art converter and font typing creator * making a cover picture * having all the pictures of stuff in game *For 0.30.0: Basic idea is to have the raw picture and then based on the size setting will print out JUST the right size ascii art to fill the screen (bassically dynamicly size ascii art) 2.0 Understand Liam's Algorithm 2.0 Modify to read in image 3.0 Get printing based on dynamic inputs and sizing from settings and integrate into code | 0.30.0 part 0.30.9
51 | 0. ~ |  | 2 | Text/Grammar/Naming | * Spelling and grammar check before release (maybe needs a text output function) * Don't except empty name * "B is back" (Zac) * "Dell, Intel Inside" * search keyword for search * When you inspect the car it says 'Ya thought these were the keys' * When you searching when nothings there "You double take and there's still nothing there" (If you search 20 times you die) * Make father frobenius and Mario Ponce tovar spelled right with accent | 0.30.0
52 | 4. X |  |  | Procedural Generation | Having Map/dungeons, maybe charaters, proceduraly generated
53 | 4. X | Creative Mode |  | Mod Tools | * Bassically graphical version of Creative Mode scripting * Maybe make a set of mod tools with the game? Maybe those are Excel Sheets? * CSV entity importer and code writer (helps as part of Mod Tools where you can draw map in Excel and it imports it) | 0.34? | Involved with players that can make their own stuff and post it | Creators/Creative Person
54 | 4. X |  | BD, 30? | Kipling | * Have this as kipling game for this year if they want with all people in it * April is kickoff for next game * Game would still have to be approchable by all people * Should definetly bring up as a suggestion | 0.31? | A reocurring and growing Eng Phys Game | Mac Eng students
55 | 1. ★ |  | 24 | Dev Mode/revoke info | *1.0 See if renaming files messes anything up or can keep low level hiding *3.0 For game saves have it so it saves after you attack someone so can't reload attack. Also game saves when you hit exit. You can still get around that by copying your game file but I don't think there's any way to get around that. (Easy encryption, renaming, and hiding files) python how to make a hidden folder https://stackoverflow.com/questions/549109/hide-folders-file-with-python https://code.activestate.com/recipes/303343/ https://docs.microsoft.com/en-us/windows/win32/api/fileapi/nf-fileapi-setfileattributesa?redirectedfrom=MSDN https://www.daniweb.com/programming/software-development/threads/180031/how-to-hide-a-file-using-python *3.0 for health and other stats just say: "You feel injured", "weak", "broken", "great"etc For attack just have "you feel strong!", "You're basically god", but don't have too much precision Use if statement delimeters *2.0 quest flag hitter from Consol in Devmode with quest keyword (type in name of quest) (implement like other keyword dictionary lookup) *0.5 Devmode option name to play as just doug and not Tyler Kashak *4.0 Maybe option to set stats, spawn weapons, Enemies, etc *0.5 Make it a seperate extended set of acceptable verbs so you can't even say those commands in normal play It's basically just creative mode at that point Nice to Have: * "You've unlocked the POWER of the '/' KEY. You now have the power to modify your world as you see fit.\nUse it wisely." You enable devmode with all the creative functions once you beat the game ( don't have it write DevMode to gamesettings as want it local to file and still not to be discovered) * Any multi-line inputs need '/' and gets put into creativemode script setting paramters of all types ex) /setEnemy Dr. Minnick sinfo "Dogs are not hogs" Ability to create new default items/characters in your location /createEnemy Ability to read out all object attributes, maybe later see specific ones with /seeEnemy Dr. Minnick sinfo Done: * Redact INFO/Art/Music/Map REMOVED No Ascii art (or at least until is dynamicl), no stats (stats, attack things, inspecting), music/sounds, map NOTE PAP, 10:30 left in there for the MEME but not further implemented CHANGED Only shows times if you're on speedrun mode! NOTE DO NOT BREAK IMMERSION * Dev Mode ADDED Can only use certain keywords in DevMode CHANGED Devmode make it automatically be fast test and disables openning ADDED Enter dev mode by typing 420E69 into Setting screen (say nothing), or ingame have it say "YOU dont' understand that command" Before running the game DevMode in setting.ini will need to be disabled being written in settingscreen AND command REMOVED devmode from setting Screen REMOVED self.item = None from ENEMY class ADDED Only show info that is if you're in dev mode including info from enemies and inspectibles CHANGED DevMode Doesn't make your name Tyler Kashak, makes it Doug Fallon so you don't discover. | 0.30.0 | Easy to develop but still hidden from players
56 | 2. ✔ |  | 15-22, extra 5 optional hours | Text Interprutation/Lexicon/Tutorial | * Lexicon for similar related words * There are good lexicons * there are machine learning/AI natural language processing - Brian to look into *Search for subword in sentence to accept if right things in there as long as doesn't interprut the wrong action * Worse thing in a game as a player is to know what to do but not how to do it * Have a whole user input module that deciphers input From Written Work *1. Parsing system where verb is first and then searches for noun based on context of surroundings E.g. attack Some verbs like "pick" are contextual based on selected noun, item, interact, person so will have to test. *2. Parsing looking for verb and noun in sentence based on context of surrounding * Be able to use any part (space delimited) of the name if an item, interactable, or enemy in the spellchecker and acceptor as long as it only closely matches one *Spell check will have to look at the important words and try to match based on context of surroundings (all entities in that locations) *Either way it will boil down to context of the game. There are only so many functions that words can go into. NO NEW FUNCTIONS WILL BE MADE BASED ON PARSER *WILL Need testers for parser AND it will boil down *Can Break this down into time with lots of time to developed and test *Multiple rules signs with different aspects When you first load in it explains accepted words Movement infront of JHE Talking and Reading (read everything) with Kenrick (spawns things) Inspecting things and talking to people (quests) in BSB field with msp430 and trash can and also Mitch with his cell phone or keys or Wallet Explain how talking or completing quest can unlock/spawn people. There are different ways to get what you want, sometimes you can talk, sometimes all it takes is getting something, but other times you need to take it by force Attacking things in JHE field with low-level person like a dummy or something shortcuts and settings On notes if they are added Feedback, bugs, offensive contents and updates! Overview of game functions • Nice to have is after you read the sign and copy it down in your notes it disappears • You can examine people (just says that's Dr Summerville, it's rude to state"), places (gives you lore and looks around again), and things (Items and injectables) • first message explains parsing and inspecting and says "to learn more, look at that tutorial sign" | 0.30.0 | Text Based Adventure! Rewarding for players to figure out | Adventurers
57 | 2. ✔ |  | BD |  | Found out you can clear screen, colour, maybe even change font size Using colourize module utilizing ANSI escape coding This means not only text background and forground can be done (probably through printT/writing characters BUT YOU CAN CLEAR THE SCREEN WHICH MEANS ANIMATIONS AND UPDATING SCREENS Might be concern you may want to be able to go back and read things. IDK This also means screen can probably read out characters one by one... Also never considered possibility of having MULTIPLE text terminals (might need to open ports?) https://www.devdungeon.com/content/colorize-terminal-output-python https://stackoverflow.com/questions/3592673/change-console-font-in-windows https://en.wikipedia.org/wiki/ANSI_escape_code#DOS_and_Windows https://liferay.dev/blogs/-/blogs/enable-ansi-colors-in-windows-command-prompt Still to investigate: python change terminal font pythong change terminal bold python change terminal background picture | 0.30.0 | Good Looking | Anyone
Liam Suggestion to do Open source Python project
Actively kept TODO with skill difficulty and maybe time
Could be whole issues list thing
|  |  |  | Want to get done before december when python 2 support ends |  |  |  | Github page for open source python rpojects to get ideas
|  |  |  | aaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaa |  |  |  | Difficulty is a good metric because agnostic to person using it
|  |  | Put priorties/finish list |  |  |  |  | Start by being helpful and not doing code
|  |  | Fix Description List |  |  |  |  | How to start python opensource project
Integrate bug/must have from feedback
Integrate TODO list
Fully Integrate (and delete) EBTA Written Work
Breakdown big ones
|  |  | Compile big list |  | Finished Feature lock so all future features go marked as not in this update
Layout roadmap/plan document
Games/projects need synthergy to be more than the sum of their parts
Maybe consider doing half release with all mechanics then rest of 2019 Kipling in the (maybe 0.30.0 and 0.30.5 or just 0.30 and 0.31)

## Alpha 0.30 Feature List
Alpha 0.30 - 2 Updates
0.30.0 | Half Release | Features + Updated 2017-2018
0.30.9 | 2019 Kipling | 2018-2019 story
0. Class Level
Idea is to get stabely working game with 0.30.0 then build onto it with 2019 version | [8 empty] | 1. Features/mechanics
2. GUI
3. Compiler
4. Content
0.30.0 Feature List | [8 empty] | 5. Balance
For details see feature lock
Feature Number | Priority | Level | Est. Time | Feature | Notes | 0. ~ | 0. Bug | 0. Class Level | 0. Class Level | hard and priority features first so get idea of timeline
50+51 | 0. ~ | 4. Content | 8 | Map/Item/People/Quests/Text/Grammar/Naming/Bugs | All Feedback and Bugs | 1. ★ | 1. Must Have | 1. Features/mechanics | V | build from ground up for foundation/bug sake
56 | 1. ★ | 0. Class Level | 15-22, extra 5 optional hours | Text Interprutation/Lexicon/Tutorial |  | 2. ✔ | 2. Try, see how far | 2. GUI | 1. Features/mechanics | (i.e. don't want big feature at end that breaks game and causes big rebuild)
55 | 1. ★ | 0. Class Level | 24 | Dev mode/revoke info |  | 3. ☺ | 3. Nice to Have | 3. Compiler | V
16 | 1. ★ | 1. Features/mechanics | 8 | Auto Descriptions |  | - |  | 4. Content | 2. GUI
48 | 1. ★ | 5. Balance | 10-18, 20 | Boss Balance |  | - |  | 5. Balance | V
22 | 2. ✔ | 3. Compiler | 7 | Proper Compile |  | - |  | - | 3. Compiler
5 | 3. ☺ | 0. Class Level | 20 | BioCards | Need Tyler and Mitch's help to write | - |  |  | V | SO THE PLAN HAS CHANGED
18 | 3. ☺ | 0. Class Level | 20 | Quest Navigation | SUPER nice-tohave/non-prirority, LOTS of interface work | - |  |  | 4. Content (items, quests, people) | 0.30.0
50 | 3. ☺ | 1. Features/mechanics | 7 | Scaling Art + Artwork ascii converter | Can get Liam's help to work with his module | - |  |  | V | MAKE 2017-2018 a Text Based Adventure to its fullest degree to captalize on things that make it great
25 | 3. ☺ | 2. GUI | 10 | Ingame Settings |  | - |  |  | 5. Balance | Lean into story
28 | 3. ☺ | 5. Balance | 19-20 | Item, story, Mechanic Balance/Expan |  | - |  | Always is highest level it affects |  | Get rid of info that's not immersive
|  |  |  | aaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaa |  | - | Standardize before optimize (get it working before pretty) |  |  | DO NOT BREAK IMMERSION
|  |  | Total Times |  |  | - |  |  |  | So this is good and bad, priorities have changed. I think 2017-2018 will end up the best version of itself and not a launching board for 0.30.9
|  | 0. ~ | 8 |  |  | - |  |  |  | BUT this does mean possibly more work, more focus on playability/balance, and much more design to anticipate the user
|  | 1. ★ | 57-79 |  |  | - |  |  |  | And a lot of features will be pushed to 2018-2019 version and it becomes a different game
|  | Min Work | 65-87 (100)hours |  |  | -
|  | 2. ✔ | 24 |  |  | - |  |  |  | 0.30.9
|  | Happy | 89-111 (120) hours |  |  | - |  |  |  | This game is a full mud McMaster Eng Phys Multi-User Dungeon (MEPMUD), MEMUD for short
|  | 3. ☺ | 60 |  |  | - |  |  |  | These features will cator to an rpg with text-only ellements (for the meme, not necisarily because I don't want to do graphics but I still don't want to make them, oh wait but I will but just convert them to text? Fuck)
|  | Very Happy | 149-171 (200) hours |  |  | - |  |  |  | Tyler likes the idea and how it goes to the whole story
[6 empty] | - |  |  |  | Need Tyler for writing, Liam for mechanic advise
[6 empty] | - |  |  |  | Both seem interested to that capacity
0.30.9 | [5 empty] | -
Learn Pygame | [5 empty] | - |  |  |  | Bring in consultants for feedback or help each section:
Year Selector | [5 empty] | - |  |  |  | Liam and Tyler for feature lock
MAP/Characters | [5 empty] | - |  |  |  | Erik+Zack for music and sound effects
Storyline/quests | [5 empty] | - |  |  |  | Liam F., Tyler, Zack, Brian, Hannah, and Liam D. For 2019 storyline
[6 empty] | - |  |  |  | Eric, Tyler, Brian, and Liam for looking and GUI and half release of 0.30.0
Intro | [5 empty] | - |  |  |  | Brian for natural language interpreter
BSB Dungeon | [5 empty] | - |  |  |  | Tyler for writing
Tutorial | [5 empty] | - |  |  |  | Liam for Mechanics/features
-
Minigames | [5 empty] | -
PAP Unlock | [5 empty] | -
Interriors
EXP/LVLs/Mobs
GUI
Fast Addrewssing
Music/Sounds
Time
NPCs
Artwork
Balance/bugcheck

## Alpha 0.30 Scheduling
Alpha 0.30.0 Schedule
Features are in Order |  |  |  | For details see feature lock
Feature Number | Priority | Level | Est. Time | Feature | Notes |  |  |  | Est. Time | Feature
55 | 1. ★ | 0. Class Level | 24 | Dev mode/revoke info |  |  |  |  | 24 | Dev mode/revoke info
16 | 1. ★ | 1. Features/mechanics | 8 | Auto Descriptions |  |  |  |  | 8 | Auto Descriptions
56 | 1. ★ | 0. Class Level | 15-22, extra 5 optional hours | Text Interprutation/Lexicon/Tutorial |  |  |  |  | 15-22, extra 5 optional hours | Text Parser/Tutorial
22 | 2. ✔ | 3. Compiler | 7 | Proper Compile |  |  |  |  | 7 | Proper Compile
50+51 | 0. ~ | 4. Content | 8 | Map/Item/People/Quests/Text/Grammar/Naming/Bugs | All Feedback and Bugs |  |  |  | 8 | Known Bugs + Feedback
28 | 3. ☺ | 4. Content | 19-20 | Item, story, Mechanic Balance/Expan |  |  |  |  | 19-20 | Story Expansion
48 | 1. ★ | 5. Balance | 10-18, 20 | Boss Balance |  | 82-90 (25 optional hours) | Here is where we want to get to |  | 10-18, 20 | Boss Balance
50 | 3. ☺ | 1. Features/mechanics | 7 | Scaling Art + Artwork ascii converter | Can get Liam's help to work with his module |  |  |  | 10 | Ingame Settings
25 | 3. ☺ | 2. GUI | 10 | Ingame Settings |  | 20 hrs | Getting here is great and helps extra game |  | 7 | Dynamic Ascii Art
5 | 3. ☺ | 0. Class Level | 20 | BioCards | Need Tyler and Mitch's help to write |  |  |  | 20 | Quest Journaling
18 | 3. ☺ | 0. Class Level | 20 | Quest Navigation | SUPER nice-tohave/non-prirority, LOTS of interface work | 20 hrs | Only if somehow have lots of time |  | 20 | BioCcards
|  |  | Total Times |  |  |  | Let's say finish scheduling by October 7th
|  | 0. ~ | 8 |  |  |  | 34 | Days between October 8th and Nov. 11st when it's due
|  | 1. ★ | 57-79 |  |  |  | 17 | HOURS at 30 mins a day/3.5 hr/week
|  | Min Work | 65-87 (100)hours
|  | 2. ✔ | 24 |  |  |  | Med End let's say
|  | Happy | 89-111 (120) hours
|  | 3. ☺ | 60
|  | Very Happy | 149-171 (200) hours |  |  |  | High end let's say
[7 empty] | 5 | 4 day 'free' weekdays
35 | Hours Learn Pygame (11.5 hours of actual video, maybe double or triple amount of time to write/learn/read documentation), 30 hours | [5 empty] | 5 | 3 day work weekends
15 | Hours Debugging, polishing, and getting into release state | [5 empty] | 35 | Days In total
[7 empty] | 60 | If 6 hours (two 3 hour sessions) per 'free' weekdays
Let's say the estimates are right, they're not, they'll take WAY longer | [6 empty] | 15 | If 1 hour per weekend
Level | Hours | Hours per week |  |  |  |  | 75 | Hours upper limit IF I'M PUSHING IT at 43 hours a week
Min Work | 150 | 30 | [5 empty] | Maybe going crazy get 300 hours SOMEHOW
Happy | 170 | 34
Very Happy | 250 | 50 |  |  |  |  | So anywhere between 17-75 hours left
Let's go somewhere and say we have about 50 hours
Okay Let's stop worrying about how many hours per week/day and actually start doing as much IMPORTANT things as early as possible to get time advantage. | [6 empty] | Jesus crist that's not a lot of time
Total Schedule Planning
Let's say finish scheduling by October 7th
85 | Days between October 7th and December 31st when it's due
42.5 | HOURS at 30 mins a day/3.5 hr/week | the low end/garunteed hours commited to the assignment (not a lot at all)
Med End let's say
High end let's say
12 | 4 day 'free' weekdays
12 | 3 day work weekends
84 | Days In total
144 | If 6 hours (two 3 hour sessions) per 'free' weekdays
36 | If 1 hour per weekend
180 | Hours upper limit IF I'M PUSHING IT at 43 hours a week
Maybe going crazy get 300 hours SOMEHOW
So anywhere between 40-275 hours left
Let's go somewhere and say we have about 100 hours
Jesus crist that's not a lot of time

## Alpha 0.30 Milestones
Milestones
For timeline I worked from where I was forward, priority if finishing this game and then we'll try to get as much as we can with the next one!
Make milestone dates based on constraints and busyness with work and factoring in that things take a lot longer than you think
Objective Date | Milestone
October 7th | Alpha 0.30.0 Feature Lock List, Breakdown, Schedule+Plan Done
October 9th | Feature Lock Review
Oct 30-Nov 3 | Hollywood Internal Playtest
Nov. 4-10 | Alpha 0.30.0 Polish Week (review, feedback, polish, finish, release), start breaking down 0.30.9 if you're comfortable
Nov. 6-9 | Alpha0.30.0 Playtest/feedback
November 11th, 2019 | Last EPTA Update Alpha0.30.0 Final Compile and Release
Nov. 16th? | Hollywood U Presentation
Nov. 11th, 2019 | Alpha 0.30.9 Feature Lock List, Breakdown, Schedule+Plan Done
Nov. 16th | Pygame Tutorials Complete
Dec. 4th or Nov 27th | Mid 0.30.9 Progress Review (check direction, design, and schedule for last month)
Dec 12-14th | Alpha 0.30.9 1st Hollywood Internal Playtest
Dec 18-21st | Alpha 0.30.9 MEPMUD 1st Beta Test
Dec 24-30th | Alpha0.30.9 Polish Week
Dec 28-29th | Alpha0.30.9 MEPMUD 1st FULL Play Test (compiled)
December 31st, 2019 | Possible Last Update, BETA Final Compile and Release
Dec 31, 2019 Final Possible Release

## Alpha 0.30.0 Parser
Parser Maddness Breakdown
I want to make the best game possible, but have to understand code that's being put in or the system I'm going to use. That's going to take time and we've only really have a couple weeks.
Do research on what other systems have to offer, if open source can use some of their code.
It's a time tradeoff, if I find the perfect thing or near it that I can modify I'll try to remake the game in that.
If not I'll try to understand other text parsers and their systems
It's a good idea to explore what the IF (Interactive Fiction, also known as Text Adventure) or MUD communities has done. Even ask questions and engage with them.
Due to the unknowns of rewriting in an authoring will be finishing up this month in Python. It will be nice to have to understand and implement better parsing (see the other decode examples, in-depth decode python examples, read literature on it) but for now am going to make it a lower priority. It will still be a possible goal after its done to implement using Inform or TADS or even PAWs but right now will be a level 2 priority (system 0-2 based on outline) that we will outline and come back to at the end if time.
I'll research tomorrow and bit of Sunday about features of this each authoring and easy of implementing those features BUT Monday is the EBTA plan deadline. I would rather spend time outlining a parsing system I know and can test if it will work
See the TONS of not only information but authoring systems (engines) and contests in the interactive fiction (IF) community